## Requirements Stack
REQUIREMENTS STACK:
Requirement ID | Description | Story Points | Priority | Sprint Number | Story Point Totals | Notes | Total story points estimated:
1 | Choose model (Hugging Face) | 3 | 1 | 1 | 33 |  | 155
2 | Find image dataset to train model on | 3 | 1 | 1
3 | Find text dataset to train model on | 3 | 1 | 1 |  |  |  | name teehee
4 | Train model on dataset | 21 | 1 | 1 |  | We have little reference for how long it will take to train model on datasets specific to our purposes, so it likely won't take 21 points, just a placeholder for uncertainty |  | objective
5 | Design output data format | 3 | 1 | 1 |  |  |  | novelty
6 | Image->alt-text intermediate step | 5 | 1 | 2 | 31 |  |  | last week
7 | Create text webscraper | 5 | 2 | 2 |  |  |  | next week
8 | Create image webscraper | 5 | 2 | 2
9 | Interpret text scraped data | 5 | 2 | 2
10 | Interpret image scraped data | 5 | 2 | 2
11 | Create function interface for scraper | 3 | 2 | 2
12 | Test model on scraped data | 3 | 3 | 2
13 | Choose front end framework (Flask) | 2 | 3 | 3 | 28
14 | Design front end UI | 5 | 3 | 3
15 | Create front end | 8 | 3 | 3
16 | Back end integration with front end | 13 | 3 | 3
17 | Create API for embedded use | 21 | 4 | 4
18 | API Integration and Testing | 21 | 4 | 5
19 | Existing alt-text predictive verification | 21 | 5 | 6 |  | Subject to dropping if we need to push any of the previous sprints further than expected

## Agile Reference Stories
AGILE REFERENCE STORIES:
Ref Story no. | Story pool/bucket | Story source | Summary |  | 1,2,3,5,8,13,21
1 | 5 | EECS 581 Project 1 | Setting up the game environment: creating classes for each object in the game, A ship, a player, a board, and a game instance. Along with all of the functions inside that would be needed, i.e for player a sunk ship checker to see if any ships aren’t sunk | Number of 1s | 3
2 | 13 | EECS 581 Project 1 | The main game loop logic using the setup give: create logic for player turns, functions to do display, functions to create ships for players | Number of 2s | 3
3 | 2 | EECS 581 Project 1 | Drawing ships: Add logic to convert board coordinates to on screen pixels to allow for accurate ship appearance. Orient the ship according to how it's placed on the board. Create function for drawing ships each turn based on the active player. | Number of 3s | 3
4 | 3 | EECS 581 Project 1 | Destroying a ship: logic to sink a ship, once all sections of a ship have been hit, create some way to confirm that the ship has sunk, either a method or an attribute. | Number of 5s | 4
5 | 3 | EECS 581 Project 1 | Displaying per player: Create a system to use display logic to show only one players ships at a time. If player 1 is active, show all shots taken on both boards, but only show player 1’s ships on the correct board. | Number of 8s | 4
6 | 8 | EECS 581 Project 1 | Ending the game: once a player has sunk all of the enemies ships, display the win screen with that player's number displayed as winner. If player 2 has no ships unsunk, then display win screen for player 1. | Number of 13s | 3
7 | 13 | EECS 581 Project 2 | Ai opponent: create an ai opponent with 3 levels of difficulty. Easy where it shoots randomly, medium where it shoots randomly until it hits something, at which point it shoots orthogonally to sink a ship, and hard, which just shoots every ship coord in order. |  | 0
8 | 2 | EECS 581 Project 2 | Super shot: create an option to do a 3x3 shot for the player. Shot shoots in a 3x3 square centered on given coords. b2s would result in a1-c3 being shot. Shots off the board are ignored.
9 | 3 | EECS 581 Project 1 | Ship placement logic: checking not only if the selected coordinate is a valid placement but also the coordinates the ship extends into are valid as well. If not, ask the player to replace the ship until they give a valid placement.
10 | 5 | EECS 581 Project 1 | Creating assets: creating assets for ships, hit markers, and sunk markers so that the are the correct size and scale. Also ensure that colors are easily visible and convey information to the player
11 | 8 | EECS 581 Project 1 | User input interpretation: parse input strings to ensure valid input, then convert that input into the correct functions. Placing ships, shooting at coordinates, and using super shots
12 | 5 | EECS 581 Project 1 | PyGame setup: Create the basic structure for the PyGame class to interpret Battleship in PyGame. Includes basic methods and structure that will be used for more complex operations later.
13 | 2 | EECS 581 Project 2 | Fix previous group's errors: placing a ship that extends into an invalid coordinate makes it impossible to place any ships. Each player is able to see the opponent’s board when the turn switches.
14 | 13 | EECS 678 Quash | A Unix pipe connects the STDOUT (standard output) file descriptor of the first process to the STDIN (standard input) of the second. When the first process writes to its STDOUT, that output can be immediately read (from STDIN) by the second process
15 | 5 | EECS 678 Quash | Single commands without arguments, such as ls which lists the files and directories inside of the current working directory. Does not take any arguments or parameters following the command.
16 | 8 | EECS 678 Quash | Single commands with arguments, such as ls -a / which represent all files, including hidden files and directories in the listing. Takes one or more arguments following the command.
17 | 1 | EECS 678 Quash | Change directory: Change current working directory. This updates both the actual working directory and the PWD environment variable.
18 | 1 | EECS 678 Quash | Print the absolute path of the current working directory. Ensure printing out the actual working directory and not just the PWD environment variable.
19 | 8 | EECS 678 Quash | Jobs: print all of the currently running background processes in the format: "[JOBID] PID COMMAND" where JOBID is a unique positive integer quash assigns to the job to identify it, PID is the PID of the child process used for the job, and COMMAND is the command used to invoke the job.
20 | 1 | EECS 678 Quash | Echo with single argument: Print a string given as an argument. The output format should be the same as bash (a string followed by new line '\n')